## CHNA_ImplPlan_Draft
2022 CHNA Implementation Plan - Henry & Benton County, MO (4/1/23 to 3/31/26)
Wave #4 CHNA Health Needs Tactics Year 1 of 3 - On Behalf of Golden Valley Memorial Healthcare, HCHC & Compass
| CHNA Health Areas of Need | T | "Specific Actions" to Address Community Health Need or "Reasons Why Hospital Will Not" | Identified "Lead" | Identified Partners | Timeframe | (Hours) | $$$
0 | Community Collaboration to address all unmet health needs | a | Relaunch Henry County and Benton County Coalitions; tie community health improvements into upcoming TORCH initiatives. | HCHC, Compass, GVMH | Schools, Pharmacies, Providers, Law Enforcement, GVMH, Chambers, Cities, Counties, MO, Schools, Colleges, WCCAA | 2023-07-01 | 60 | 5000
|  | b | Continue CHART coalition development championed by health departments, Compass, GVMH. | HCHC | GVMH, Compass | 2023-05-01 | 24 | 6000
1 | Substance Abuse (Drug/Alcohol/Nicotine) | a | Provide tobacco/drug/alcohol education to students (i.e., Health Department, etc.) and increase school-based programs. Apply for grants. Work with the health education classes. | HCHC/ Compass | Schools, Pharmacies, Providers, Law Enforcement, GVMH, Chambers, Cities, Counties, MO, Schools, Colleges, WCCAA, Birthing Center at GVMH | 2023-06-01 |  | 1000
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Build Recovery support system partners. Create programs to help addicts and their families. Continue to provide counseling and support for drug abusers and their families. Support local substance abuse counseling. Educate public on signs of drug abuse and how to approach those needing guidance. | Compass | GVMH, HCHC, Law Enforcement, Schools
|  | c | Monitor prescription drug abuse. Support PSA providers in discouraging prescription drug abuse. Educate new providers on system. | Compass/ GVMH | HCHC, Law Enforcement | 2023-04-01 |  | 2000
|  | d | Investigate grant writing to fund Drug Abuse education/counseling. If available, designate community lead to work to attain the necessary grant. | Compass | GVMH, HCHC
|  | e | Promote discarding old prescriptions (prescription take-backs) at local law enforcement agencies and health departments, especially opioids. | HCHC/BCHD | Compass, GVMH, Law Enforcement | 2023-07-01 | 8 | 500
|  | f | Continue to develop pain management programs and GVMH steering committee. Meet with partners to assess the current needs and initiatives. Continue to educate providers on alternative pain control resources. Provide community outreach awareness and education on alternative pain control resources. | GVMH | Providers in PSA | 2023-04-01 | 120 | 12000
|  | g | Continue to promote Recovery Court in PSA Clinics. Expand this service to Benton County. | Compass | GVMH, Law Enforcement, Pro Attorney
|  | h | Promote and expand awareness of suboxone treatment services. | Compass | GVMH, Providers in PSA, Law Enforcement
|  | i | Continue to utilize HCHC grant $$ funding to set programs up in schools in PSA. Continue DARE program. | HCHC | Schools, Law Enforcement | 2023-07-01
|  | j | Consider expansion of screening brief intervention referral and treatment (SBIRT). Promote evidence-based interventions. | Compass | GVMH, Providers in PSA
|  | k | Continue Rural Community Opioids Response Program (RCORP). | Compass | GVMH
2 | Psychiatric IP Beds (Access) | a | Promote and optimize ERE Program at GVMH to benefit residents in the PSA / address unmet need. | Compass/ GVMH | Law Enforcement, Providers, EMS | 2023-04-01 | 2080 | 50000
|  | b | Retain existing psychiatric providers and determine if additional providers should be recruited. | Compass/ GVMH | Independent BH Providers | 2023-04-01 |  | 100000
|  | c | Continue to recruit providers to area. Utilize national recruiters to find quality providers. | Compass/ GVMH | Katy Trail, Bothwell Regional Health Center | 2023-04-01 |  | 100000
|  | d | Evaluate and possibly expand Inpatient Adult/Geriatric Behavioral services. | Compass/ GVMH | DHSS, Mo Legislature | 2023-04-01
|  | e | Continue to promote Royal Oaks Hospital (14 beds) in Windsor. Utilize their services within both counties. Consider opening additional IP beds. | Compass/ GVMH | DHSS, Mo Legislature | 2023-04-01
3 | Nursing Home (Available/Quality) | a | Research further Nursing Home/Senior health issues. Start local task force to address access, quality and cost issues. | Avant-Guard (AGH), GVMH | Lincoln Community Care Center, Adair Village, CHRC, Warsaw Healthcare, AGH | 2023-04-01 | 24 | 5000
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Begin a county-wide Healthy Seniors Club. Establish programs, housing and services to allow older adults to "age in place." Coordinate with senior center. | HCHC | GVMH, Compass, Senior Centers, DHSS, Senior Tax Board, City/County Government | 2024-08-01 |  | 5000
|  | e | Explore the expansion of senior transportation services while looking into expansion of services for Healthcare and Mental Health utilizing WCCA. | WCCA | GVMH, Compass, HCHC, City/County Government |  |  | 1
|  | f | Explore starting the a "Adopt a Senior" Program in the county. | HCHC | GVMH, Compass, Schools, College, Civic Orgs | 2024-08-01
|  | g | Continue Tele-Health program for homebound patients. Explore Tele-Health opportunities for home health. | GVMH | Providers in PSA | 2023-04-01 | 500 | 100000
|  | h | Work with local discharge planners to coordinate and streamline placement. | GVMH | Providers in PSA, Nursing Homes | 2023-04-01 |  | 50000
|  | i | Increase access to in home, nursing home, and assisted living care. | Avant-Guard (AGH), GVMH | Lincoln Community Care Center, Adair Village, CHRC, Warsaw Healthcare, AGH | 2023-04-01 | 24 | 5000
|  | j | Seek seed grant money to support the exploration of transitional living program development. | City/County Government
4 | Housing (Affordable/Safe) | a | Complete Henry and Benton county-wide housing study. Create a County Housing Development Plan that would address affordable safe housing for community residents. | PSA Counties/ Cities | WCCAA, HCHC, Counties, Compass, GVMH, Chambers, Harvesters, Kaysinger Basin, MU Ext, Schools, Colleges
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Explore and create a coalition to investigate Habitat for Humanity-type process in Henry and Benton county area. | City/County Government, HCHC
|  | c | Develop housing coalition properties to enhance housing in PSA. Explore safe rental inspections setups. Reinstate code officer. | City/County Government
|  | d | Investigate grant writing to fund public / safe housing. If available, designate community lead to work to attain the necessary grant. | City/County Government
|  | e | Target infill development of existing infrastructures to encourage affordable home ownership. | City/County Government
|  | f | Continue WCMAA voucher program, FSS program, HUD and weatherization programs. | WCCA
5 | Community Education (Mental Health/Anxiety etc.) | a | Continue to build community BH education program. Collaborate with community elementary, middle and high schools to educate students on mental health (destigmatize mental health conditions, suicide prevention and social media bullying). | Compass/ Schools | GVMH, Law Enf, MO, Cities, Counties, Colleges, HCHC, Kaysinger Basin, MU Ext, WCCAA
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Promote a Community Inventory of Services to document the availability of mental health resources, including hours of service. Have HCHC host BH Inventory via web for public access. Document mental health services by age categories. | HCHC/ Compass | GVMH, Compass, independent BH providers
|  | c | Continue Mental Health care support at clinics. Increase depression screenings by PCPs. Add provider training related to trauma assessment for pediatrics and other MH issues. Include education related to suicide risk for nondepression complaints. | Compass/ GVMH | Children's Mercy | 2023-07-01 | 60 | 5000
|  | d | Investigate grant writing to fund mental health education and services. If available, designate community lead to attain the necessary grant. | Compass/ GVMH | HCHC, Law Enforcement | 2023-10-01 | 20 | 2000
|  | e | Partner to improve mental health service "first aid" training for law enforcement, schools and other first responders in the community. Expand to community members. | Compass
|  | f | Continue Suicide prevention training at schools. Develop and sponsor an antisuicide campaign for local community members. | Compass
|  | h | Continue to grow School Counselors (Compass partnership) in Clinton Schools. Expand into Warsaw and Clinton school districts. Recruit for Social Workers, Counselors and MH Providers in schools. | Compass
|  | i | Continue to have Law Enforcement / Providers complete CIT training (20 hour training). Encourage participation to attend monthly meetings (MissouriCIT.com). | Compass/ GVMH | Law Enforcement, Providers, EMS
|  | k | Continue with Compass Crisis training on school campuses to support BH crisis intervention program. | Compass | Schools, Law Enforcement
|  | l | Continue with MU Ext Youth MH Course offerings. | MU Extension
|  | m | Continue to offer and promote the QPR Compass Program for community members. | Compass
6 | Chronic Disease Management (COPD, Diabetes, Cardiac and Cancer) | a | Continue to develop processes that support primary care and other providers in efforts to refer patients to nutritionists and diabetic educators. Identify chronic disease nursing support. | HCHC, Compass, GVMH | Schools, Pharmacies, Providers, Law Enf, GVMH, Chambers, Cities, Counties, MO, Schools, Colleges, WCCAA, Birthing Center at GVMH | 2023-04-01 | 4160 | 120000
|  | b | Explore utilizing chronic patient monitoring at home. Investigate Mobile APP support. | GVMH | CoMo Connect, Cellular Providers | 2023-04-01 | 2080 | 50000
|  | c | Utilize / explore additional grants already in place for Blood Pressure Cuff and Chronic Care. | GVMH | MHA, DHSS, Compass | 2023-04-01 | 50 | 5000
|  | d | Investigate the further usage of telemedicine to help with chronic disease management. | GVMH/ Compass | ISPs, Cellular Providers, Providers | 2023-04-01 | 1040 | 25000
|  | e | Actively participate in the Medicare chronic disease program. Coordinate participation in program and investing in resources (capital and Information systems) necessary to support the program. | GVMH/ Compass | Aledade ACO, Providers, DHSS, Commercial Payers | 2023-04-01 | 4160 | 250000
|  | f | Continue GVMH support groups for diabetes, cancer and cardiac rehab. | GVMH | Providers | 2023-04-01 | 360 | 12000
|  | g | Continue the development of full cancer services (i.e., chemotherapy, RAD therapy and hospice). | GVMH | Providers | 2023-12-01 | 5000 | 16000000
7 | Transportation (All) | a | Continue to research current transportation resources and gaps. Make recommendations on solutions. | WCCAA, HCHC | Compass, GVMH, HCHC, MO, Cities, Law Enforcement (CIT), Counties, Schools, Colleges | 2023-06-01
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Communicate to the public what transportation services are available through mass media, online, digital and at businesses in two counties. | WCCAA, HCHC |  | 2023-06-01 |  | 500
|  | c | Seek transportation grants for Henry and Benton County. | WCCAA, HCHC |  | 2024-08-01
|  | e | Continue to utilize OATS, ALS - City, Health Tran, Compass services and others. | City Government
|  | f | Continue to develop the volunteer drivers program (Kaysinger Health Transits). | WCCAA, Kaysinger Basin | Compass, GVMH
8 | Urgent Care Services (After Hours) | a | Explore the feasibility of expanding clinics' after-hours care program to allow for more walk-ins. Explore whether local providers can work extended hours. | Compass, GVMH | Providers | 2023-04-01 | 2080 | 50000
|  | b | Conduct further research on the Urgent Care market desire/need. Create a Proforma to assess further services.. | GVMH | BKD | 2023-08-01 |  | 50000
|  | d | Seek additional Federal and State grant money to support additional clinic access. | GVMH, Compass | DHSS, Mo Legislature | 2023-10-01 |  | 5000
|  | e | Explore possible urgent care delivery model (Fast Track) @ GVMH to lessen ER room volumes. | GVMH | APP | 2023-06-01 |  | 100000
9 | Senior Transitional Living | a | Organize/start local task force to address access, quality and cost issues. Research further Nursing Home/Senior health issues and HC handoffs. | PSA Economic Dev, Agency on Aging | Senior Tax Board, Triple A, West Central Communications Action Agency, Missouri Department of Senior Services |  |  | 1
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Begin a county-wide Healthy Seniors Program. Establish programs, housing and services to allow older adults to "age in place." Coordinate with senior center. |  | GVMH
|  | c | Conduct feasibility study to document need of SR services and staffing/development. |  | GVMH |  |  | 1
|  | d | Continue supporting senior activities with Senior Center. Work together to establish new senior activities/programs for them to engage in. |  | GVMH
|  | e | Explore/develop senior healthcare and mental health local transportation services. |  | GVMH
|  | f | Seek seed grant money to support the exploration of transitional living program development. |  | GVMH
|  | g | Increase access to in home, nursing home, and assisted living care through community outreach programs. |  | GVMH
|  | h | Host a meeting with all nursing home facilities and local providers to share service offerings quarterly. Continue to promote local healthcare / self-service programs. |  | GVMH
10 | Food Insecurity (Healthy Foods/Education) | a | Collaborate with health plans, local cities and other groups focused on fitness, healthy eating and access to fresh fruits and vegetables. | HCHC / MU Ext | WCCAA, Harvesters, GVMH, Schools, Colleges, Cities, Counties, Clergy, Chambers, Kaysinger Basin, WIC, Fitness Centers, Compass, 4H Clubs, Samaritan Center | 2024-01-01
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Grow and promote community farmer's market. Offer gardening classes. Support “Farm to School” program to provide local produce to students. | City/County Government, MU Extension
|  | c | Expand free cooking classes to community. Create and publish health low-cost recipe book outlining healthy dinners and/or dining with diabetes/food restrictions. |  | GVMH
|  | d | Create and follow up on a community garden where locals can grow and produce their own food to decrease meal costs and increase healthy eating.
|  | e | Continue to develop support for local food bank and/or other food giveaway options. Utilize harvesters and various church giveaways. |  | GVMH
|  | f | Continue to promote community health. Create effective media (i.e., print, radio, digital). Continue to provide education to the community through health fairs and educational programs, including various screenings. | HCHC | Compass, GVMH, Providers |  |  | 1000
|  | g | Expand the Community Wellness Committee's (CWC) initiatives previously established and help implement the strategy.
|  | h | Continue the wellness incentive for GVMH, HCHC and Compass employees and launch "staff health" challenge. Continue to offer healthy food options on campus. | GVMH, Compass, HCHC | Local Employers | 2023-04-01 | 2080 | 50000
|  | i | Continue with Nutritional Education classes (MU Ext), Nutrition Services (GVMH) and IP Compass services. | GVMH, MU Extension, Compass | Community Center, ADA, Senior Center, Schools | 2023-04-01 | 4160 | 120000
|  | j | Continue to promote WIC and food stamp programs. Continue with School Backpack program. Expand "No Kid Hungry" initiative in Clinton Schools. Expand program into Benton County. | HCHC, Schools |  | 2023-07-01
|  | k | Continue and encourage other schools to provide healthier options in school vending machines. | HCHC, Schools |  | 2024-07-01
11 | Wellness Programs | a | Relaunch County School/Health Department Monthly Wellness Challenge to bring people together to participate in wellness/exercise activities. | HCHC | GVMH, Compass, Schools, College, Civic Orgs | 2024-01-01 |  | 500
|  | b | Continue Reminder Program to encourage residents to visit their providers regularly for preventative screenings and expand follow-ups to improve delivery/individuals owning their health. | GVMH, Compass | Media Outlets | 2023-04-01 |  | 100000
|  | c | Promote Community Health programs via centralized HCHC website. Use both traditional and digital media to share content to all generations. | HCHC |  | 2023-06-01
|  | d | Educate local businesses on the benefits of offering wellness programs for employees and/or community. Provide education to employers through worksite health fairs and educational programs, including various screenings. | HCHC |  | 2024-08-01 |  | 1
|  | g | Emphasize health education with focus on chronic health, smoking/tobacco/vaping, increased seat belt usage, exercise, nutrition and sex education. | HCHC |  | 2023-03-01 |  | 2000
| Overall Total Contributions | [6 empty] | 17389504

## KEYStakeholders
Henry & Benton Co, MO Stakeholders
xx | KEY | Organization | Contact | Email
f | GVMH | Golden Valley Memorial Healthcare | Craig Thompson, others | cthompson@gvmh.org
f | Compass | Compass Health Network (Henry and Benton) | Donni Kuck, Saundra Overton, others | dkuck@compasshn.org; soverton@compasshn.org
f | HCHC | Henry County Health Center (FQHC including WIC) | Peggy Bowles, others | peggy.bowles@lpha.mo.gov
v | Assisted Living | Americare, Jefferson Gardens/Glendale Gardens | David Lee
v | Chambers | Clinton Chamber of Commerce or City of Warsaw | David Plumlee (Chamber Director Clinton); Warsaw Chamber | mark@clintonmo.com; debby@clintonmo.com; warsawchamber@outlook.com
v | Cities | Clinton, Warsaw | Clinton (Christina Maggi), Warsaw (Randy Pogue) | cmaggi@cityofclintonmo.com; randy.pogue@welcometowarsaw.com
v | Clergy | Ministerial Alliance | Clinton UMC | office@clintonumc.net
v | Clubs | 4H Clubs +++, Hope Project, Zoe's House, BBBS Henry County | Henry County 4-H Council officers: Co-Presidents -- Brendon Engeman and Jessalyn Caple (MU Extension Susan Jones-Hard) | Mu Ext email
v | Colleges | SFCC, UM, CMU | Dara Bigler, SFCC | dbigler@fccmo.edu
v | County (2) | Henry and Benton County, MO
v | Drug/Alcohol | Compass
v | Ec Dev | Economic Development - Clinton | Mark Dawson | mark@clintonmo.com
v | EMS | GVMH, Warsaw-Lincoln EMS, Pettis County | Mike D'Agustino | pdagostino@gvmh.org
v | Fitness Centers | PSA Community Center (Clinton)
v | Community Support | PSA Harvesters (26 county area), Salvation Army | Sheila Barkwell (The Samaritan Center) | The Samaritan Center email
v | Housing Department | Clinton Housing Authority, Henry Housing Authority
v | Kaysinger Basin Regional Planning Commission | 7 Counties (Bates, Benton, Cedar, Henry, Hickory, St Clair, and Vernon) (state initiative) | Executive Director - Sheridan Garman-Neeman, Henry County - Dale Lawler, Benton County - Steve Daleske, Susan Jones | sgarman@kaysinger.com
v | Law Enforcement | PSA City and Counties Law Enforcement (CIT training) | Chad Nepple - CPD, Rob Hills (Sheriff's Office) | c.nepple@clintonmopd.com; rob170k9@gmail.com
v | Mental Health | Compass, Pathways, Veterans Admin (VA), Steps Program
v | MO - State | State of Missouri
v | MU Ext | Missouri University Extension Office | Debbie Dody | joneshards@missouri.edu
v | Parks & Rec | Clinton Parks & Rec, Warsaw Parks & Rec | Shannon Shockly
v | Pharmacies | PSA Pharmacies
v | Providers | PSA Providers of Healthcare
v | Royal Oaks | Royal Oaks Hospital (Compass) | Erin Allee, Erica Jenkins, others | ejenkins@compasshn.org
v | Samaritan Center | Samaritan Center - Clinton | Sheila Barkwell | director@clintonsamaritancenter.com
v | Schools | Clinton Schools, PSA schools | Teresa Howard (Social Work), Stacy Pitts, Michelle Henzlik (Clinton Intermediate), Angie Lawson, Jamie McCoy (Clinton HS Counselor), Makenna Hix | thoward@clintoncardinals.org; spitts@clintoncardinals.org; mhenzlik@clintoncardinals.org; alawson@clintoncardinals.org; jamccoy@clintoncardinals.org; mhix@clintoncardinals.org
v | Seniors | Henry County Memory Committee, Triple A, Area Agency on Aging, Avant-Guard (AGH), WCMCAA, Senior Center, Agency on Aging, Arbors | Kameron Wilson, Ranae Walath
v | State | State of Missouri
| WCCAA | West Central Community Action Agency | Gwen Klass, Linda Schreck, Patty Cantrell - New Growth, Kelly Ast, Taylor Valentine | lschreck@wcmcaa.org; pcantrell@newgrowthmo.org; Kast@wcmcaa.org
| Shelter | Ann's House (Shelter/DV Women), Hope Project, Survival House, Hope House, Survival House, Golden Valley Door of Hope
v | Alternative Funding/ Grants | TORCH, Benton County Youth Coalition, Parks & Rec, Community Development Block, Senior Minor Home Repair, Compass, RCORP

## CrossoverTable
Teams | 2019 | 2022 | CHNA Health Areas of Need
A, D, E, G |  | 3 | Nursing Home (Available/Quality)
|  | 9 | Senior Transitional Living
|  | 6 | Chronic Disease Management (COPD, Diabetes, Cardiac and Cancer)
|  | 8 | Urgent Care Services (After Hours)
|  | 11 | Wellness Programs
B, C, F, H | 3 | 1 | Substance Abuse (Drug/Alcohol/Nicotine)
| 4 | 2 | Psychiatric IP Beds
| 7 | 4 | Housing (Affordable/Safe)
| 1 | 5 | Community Education (Mental Health/Anxiety)
| 8 | 7 | Transportation (All)
| 5 | 10 | Food Insecurity (Healthy Foods/Education)